PIMCO × Bellwether Investor Portal

Engineering scope — from clickable prototype to production

## Context

Bellwether Asset Management has built a clickable HTML prototype of the PIMCO investor portal. It renders the March 2026 watchlist tape — 24 active loans, $1.0B UPB, 3 on yellow watchlist — and demonstrates the full navigation and visual language for a debt-portfolio investor portal. This document scopes the work required to take that prototype to a production system Bellwether can stand up for PIMCO (and reuse for future asset-management clients).

Prototype location: static HTML/CSS/JS, 38 pages, all data hard-coded.

Prototype source files: `portal/` folder in the bellwether-tech-architecture repo.

## Architecture principles

- Read-only for the client. PIMCO never enters data into the portal — every value is sourced from systems Bellwether already manages.

- Single codebase, multi-tenant. Branding, entitled loans, and deal-team roster are config — the same portal serves every Bellwether AM client.

- Server-side filtering. Every API enforces row-level filters based on the logged-in user's entitlement; never trust the client.

- Tape-versioned data. Every read can be filtered by as-of date. UI shows the tape it's reading from.

- Embed where it makes sense. Tableau / Sigma already own the visualization layer for the reporting tiles; the portal embeds rather than re-implements.

## Scope by surface

| Surface | Prototype state | Production scope |
| --- | --- | --- |
| Home + Topbar | Static HTML; global search runs against hard-coded loan array | Wire global search to live loan catalog (sponsor, city, state, asset manager). SSO sign-in. Persist theme preference. Permission-aware tile visibility. |
| Loan Portfolio Overview | 24 loans from March 2026 tape; donuts/maturity/runoff/risk render from baked JSON; map is an image placeholder | Hook KPIs and tables to Bellwether's Sigma/data lake. Replace map with Mapbox tiles, one feature per loan keyed to lat/long. Drill-throughs honor PIMCO row-level filters. |
| Loan summary (per loan) | 3 watchlist loans fully populated; other 21 use generic template + Notes tab | Populate Covenants, Collateral, Cap Stack, Documents, Activity tabs for all 24 loans from the loan-doc store. Documents tab reads from S3/SharePoint with signed URLs. |
| Notes | Portfolio + per-loan, persisted to browser localStorage only | REST API for note CRUD with user attribution. Bellwether-owned DB (Postgres or DynamoDB). @-mentions, email/Slack notifications on tag, edit history. |
| Reporting | Six preview tiles (mock SVGs); deliverables list renders mock PDFs | Live Tableau or Sigma embeds for each tile (iframe with row-level filtering by client). Deliverables list reads from doc store; preview uses signed S3 URLs. |
| Bellwether AI (Sigma chat) | Floating button; returns static demo response | Wire to LLM (Claude / Azure OpenAI) with portal catalog as RAG context. Audit log every prompt + response. Per-tenant data scope enforced server-side. |
| Heat map | Static placeholder image | Mapbox GL JS with custom Bellwether style. Bubble = loan, size = UPB, color = rating. Click → loan summary. |
| Multi-tenant shell | Hard-coded PIMCO branding and loan list | Tenant config service: brand (logo, colors), entitled loans, deal-team roster. Single codebase serves all Bellwether asset-management clients. |

## Proposed stack

| Layer | Proposed technology |
| --- | --- |
| Frontend | React + TypeScript + Vite. Port the existing HTML/CSS into a component library; keep the visual language one-to-one. |
| Charts | Recharts or Chart.js for in-portal; iframe-embedded Tableau/Sigma for the Reporting tiles. |
| Map | Mapbox GL JS with custom Bellwether style. PMTiles for static layers if needed. |
| Backend | Node.js (Express or Fastify) or Python (FastAPI). REST first; consider GraphQL if entitled-loan filtering gets complex. |
| Database | Postgres (managed — RDS or Aurora). Tape data + notes + tenant config. Read-replicas for the analytics surfaces. |
| Object storage | S3 (or Azure Blob) for loan documents + flash reports. Signed URLs on demand; never served direct. |
| Auth | SAML SSO via Okta or Azure AD. Bellwether issues identities for both Bellwether AM and client (PIMCO) users. |
| AI | Anthropic Claude (or Azure OpenAI) via server-side proxy. Never call the model from the browser. Per-tenant prompt budgets. |
| Hosting | AWS (recommended) or Azure. CloudFront/Front Door for CDN. Vercel acceptable for the frontend if backend is on AWS. |
| CI/CD | GitHub Actions. Branch-deploy preview environments for stakeholder review. |
| Observability | Datadog or NewRelic. Sentry for frontend errors. Audit log to a separate sink (S3 + Athena). |

## Phased delivery

| Phase | Outcome | Major work | Effort (eng-weeks) |
| --- | --- | --- | --- |
| Phase 0 — Demo polish | Prototype ready for client + exec walkthroughs | Visual QA pass in dark mode; accessibility pass (keyboard nav, ARIA); print stylesheet for Covenants PDF export; mobile breakpoint | 1 |
| Phase 1 — Wire it real | Two live surfaces, real data round-trip | (a) Tableau or Sigma embed for 1–2 tiles, (b) Mapbox geo map, (c) Notes REST API with auth + Postgres | 4–6 |
| Phase 2 — Full data backplane | Every page reads live data; nightly tape ingest | Loan catalog service; tape-versioning + as-of-date; document store integration; user/permission model | 8–12 |
| Phase 3 — Production | GA: SSO, audit, multi-tenant | SSO/SAML, audit trail, tenant config service, monitoring/alerting, RBAC, runbook + on-call | 8–10 |
| Phase 4 — AI | Bellwether AI chat live with portal context | RAG over loan catalog + docs; prompt allow-list; per-tenant data scope enforcement; logging + cost controls | 4–6 |

## Data contracts to nail down

- Loan catalog — every field shown in the portal (sponsor, UPB, rate, LTV, DSCR, occupancy, maturity, rating, asset manager) must map to a tape column or computed field. Need a source-of-truth spec for the 24 fields we currently surface.

- Document index — for every loan, what documents exist (IC memo, LSR, rent roll, appraisal, etc.) and where they live. Probably an extension of Bellwether's existing doc-management process.

- Covenant trigger thresholds — which are loan-level vs portfolio-level, who can edit them, and how cure tracking is represented.

- Note model — fields (author, tag, loan, body, when, mentions), retention rules, who can edit/delete (probably author-only + Bellwether admin).

- Tenant config schema — brand assets, entitled loan IDs, deal-team roster, feature flags.

## Open decisions needed before kickoff

- Hosting platform — AWS vs Azure vs Vercel + AWS hybrid? Drives identity-provider integration.

- Embed platform — Tableau or Sigma for the Reporting tiles? Affects auth flow and licensing cost.

- Identity provider — Bellwether SSO via Okta? Azure AD? Does PIMCO want to federate their own IdP?

- Notes scope at launch — collaborative live feed (Slack-like) or audit-trail only? Affects the notification surface area.

- AI launch timing — ship the chat in Phase 1 with a narrow scope, or wait for Phase 4 once the data backplane is solid?

- Tape cadence — daily incremental or quarterly snapshot? Drives ingest architecture.

- Mobile — do we support mobile viewports at launch, or desktop-only initially?

## Recommended team

- 1 tech lead (full-stack)

- 1–2 frontend engineers (React)

- 1 backend engineer (API, data, integrations)

- 1 data engineer (tape ingest, Tableau/Sigma plumbing, half-time after Phase 2)

- 1 designer (part-time)

- 1 PM (part-time)

Total: ~4 FTE for 4–5 months to ship Phases 0–3. Add 1 FTE × 2 months for Phase 4 (AI).

## Explicitly out of scope (for v1)

- Trade execution or settlement workflows — read-only portal.

- Direct integration with PIMCO internal systems — PIMCO consumes the portal; we don't push into their stack.

- Mobile app — responsive web first, native later if demand is there.

- White-label client self-service — Bellwether configures every new client; not exposed to clients.

Next step: schedule a kickoff with engineering to size Phase 0 + Phase 1 in story-point detail and pick the hosting platform.